## Slide 1: Funders Advisory Panel
1 November 2024
Classification: CONFIDENTIAL

## Slide 2: Housekeeping Items
Virtual Meeting Etiquette:
Please turn on your camera if possible and please turn off your mic when you are not speaking. Please kindly raise your 'virtual hand' if you would like to speak, and state your affiliation first, or you can type your questions in Chat.
Competition Law and Conflicts of Interest:
Many of you are from competitor organisations. As you will be aware it is critical that we all comply with competition law. If you are in any doubt about competition law compliance you should consult your compliance team.
Discussions between the attendees should be limited to discussing issues of general concern and you must not share or discuss any information that is commercially sensitive and not in the public domain – that includes: current or future prices, strategies, matters about customers or suppliers.
You can and should share your expertise about the matters that are specific to today’s agenda and can talk about matters that are public.
If any topic is raised which you feel uncomfortable discussing, please make this known and we will immediately adjourn discussions on that point.
If you consider that you or your organisation is or likely to be affected by a conflict of interest(s), you should make this known to the Chair promptly and you should excuse yourself from any discussions where your declared conflict of interest might adversely affect your ability to provide impartial input.

## Slide 3: Agenda
Minutes of meeting – 4 October
Financial forecast
Plan on a page
Programme status update
MLA operator
MLA legal drafting update
WS3 – roundtable update
AOB

## Slide 4: Minutes from 4 October

## Slide 5: Financial forecast – Sept '24 reporting period

## Slide 6: Financial Overview
Total Costs for Sept'24 came in at £159k, roughly 32% below budget and 17% below Sept'24 forecast.
Sept'24 YTD Total Costs now stand at £418k, which is £231k below YTD budget.
Our forecasted total costs to the end of Dec'24 is now £1.48m, roughly £165k below budget.
Total cash balance as at end of Sept'24 was £1,543,797.

## Slide 7: Overall Financial Forecasts (Sept'24)

## Slide 8: Actuals vs Budget for Sept'24 – JROC Workstream Costs

## Slide 9: Actuals vs Forecast for Sept'24 – JROC Workstream Costs

## Slide 10: Actuals vs Forecast for Sept'24 – JROC Workstream Costs (Continued)

## Slide 11: Financial Forecast (Sept'24) - JROC Workstream costs

## Slide 12: Sept ’24 Billing

## Slide 13: Itemised Billing (Ex VAT) for Sept’24: WS 1 - 4

## Slide 14: Itemised Billing (Ex VAT) for Sept’24: WS 5

## Slide 15: Itemised Billing (Ex VAT) for Sept’24: WS 5 - Continued

## Slide 16: Itemised Billing (Ex VAT) for Sept’24: WS 7

## Slide 17: Plan on a page

## Slide 18: JROC programme POAP headline changes from v1.0 – v1.1
The notable changes from v1.0 (dated 15/08/24) to v1.1 of the JROC programme POAP are as follows.
WS1. Levelling Up – As per the JROC Non-order Workplan, the 2 milestones, (actions 1 and 2 in the appx) which had a deadline of the end of November 2024, ‘Publish 6mth Summary of Data Report to JROC’ and ‘Publish analysis & recommended next steps to JROC’ have been marked red as they cannot be met due to lack of data from participants. A report has been written and sent to JROC and we are pending a decision from JROC on next steps.
WS2b. Financial Crime Tools (TRIs) – As per the JROC Non-order Workplan, the milestone, (action 8) “OBL to complete the TRI Pilot on Live Payments” at the end of Sep-24, has moved out by 1 month to the end of October, to enable an extended period of data collection and analysis. This was approved at JWIG on 09/09/24 (CR ref OBL-001).
WS3. Consumer Protection – Workstream updated to align with the change request (ref OBL-002) approved at JWIG (07/10/24) which rebaselined the workstream, extending the publication of the ‘Publish Consumer Gaps Recommendation Report to JROC’ by 1-month to the end of Nov-24.
4. Information Flows – FCA work package removed from plan as it is not an OBL action/deliverable.
All Milestones referenced in the appendix of the ‘JROC Non-Order Workplan 2024 06 28’ have now been included.
All other changes are broadly cosmetic or reflective of programme delivery.
Full details of all changes can be found on slide 6.

## Slide 19: JROC Programme POAP – 18/10/24 v1.1
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1. Levelling up | API Availability & Performance |  |  |  |  |  |  |  |  |  |  |  |  | 
2a. Financial Crime Data | Fraud Data |  |  |  |  |  |  |  |  |  |  |  |  | 
2b. Financial crime tools (TRIs) | TRI Pilot – Phase 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Consumer Protection | Gap Analysis |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Information Flows | Open Banking Standard |  |  |  |  |  |  |  |  |  |  |  |  | 
5. Commercial VRPs |  |  |  |  |  |  |  |  |  |  |  |  |  | 
19
Publish 6mth Summary of Data Report to JROC
Publish analysis & recommended next steps to JROC
Publish Open Banking Standard v4.0
Standard
Refer to detailed Workstream 5 plan for further details
Monitor adoption of voluntary implementation
Publish 6mth Summary of Fraud Data Report to JROC
Publish Initial Conclusions Report to Ecosystem
TPP Engagement
Publish TRI Recommendations Report to JROC
Monitor / Report
Finalise
Draft
Data Collection
Analysis
Analysis
Data Collection
ASPSP Engagement
Publish report to JROC on ASPSP feedback
Roundtables
Initial findings report shared with FCA/JROC
Publish report to JROC on TPP feedback
Publish update on
adoption to FCA/JROC
Interim data collection status update shared with FCA/JROC / validation of feasible end date based on participant submissions
Internal OBL checkpoint updates
Initial findings report shared with FCA/JROC
Interim data collection status update shared with FCA/JROC
Roundtables
Internal OBL checkpoint updates
Publish Consumer Gaps Recommendation Report to JROC
OBL to pilot a dash-board of API RAG rating and API for data collection
TRI Pilot 2 (Data)
TRI pilot on live payments - end date
Incremental progress updates shared with FCA/JROC
Volume ramp up
JROC approval of the WS3 scope document
CR approved
Produce Report
CR approved
Roundtables
1
2
Define scope
CR approved
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | ‘JROC Non-Order Workplan’ milestones

## Slide 20: JROC Programme - Workstream 5 POAP – 18/10/24 v1.1
Workstream Substream | Work Packages | 2024 |  |  |  |  |  |  | 2025 |  |  |  |  | 
Workstream Substream | Description | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Q2 | Q3 | Q4
Governance |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5.1. Technical | Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Blueprint Action Plan |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Rollout Guidelines |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Mi Requirements |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LT Tech/Functional Roadmap |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Wave 1 / Pilot Go Live Criteria |  |  |  |  |  |  |  |  |  |  |  |  | 
5.2. Disputes | Dispute system requirements (functional & non-functional) |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Dispute System for Wave 1* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Disputes Framework |  |  |  |  |  |  |  |  |  |  |  |  | 
5.3. Industry | Participant Readiness and Engagement |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4a. MLA Dev | Procure External Legal Support* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Sector Definitions - Wave 1 |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Development of MLA v1.0* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA / Disputes Operating Model* |  |  |  |  |  |  |  |  |  |  |  |  | 
 | MLA Roadmap Development |  |  |  |  |  |  |  |  |  |  |  |  | 
5.4b. Commercial Framework |  |  |  |  |  |  |  |  |  |  |  |  |  | 
20
PLACEHOLDER – FCA/PSR approval
Publish Wave 1 readiness report to JROC
MI requirements agreed and signed-off
Publish Final Dispute system functional & non-functional requirements for Wave 1
WGC
Iterative draft cycles
Approval & publication of Rollout Guidelines
FCA/PSR decision on approach to follow for the procurement of external legal support
WGC
Update
Draft Op Model
Approval & publication of MLA operating model
Approval & publication of Disputes Framework
Level, nature, and duration of OBL activities required TBC once PSR decision made
PSR announcement on the commercial model
Placeholder schedule
Define
Refine
MLA full Bus Reqs finalised
IC
Baseline plan
Develop Phase 1 Delivery Plan
WG’s in place (fortnightly cadence)
Establish & run VRP Working Groups
Draft
Comprehensive progress update on WS5 to JROC (PSR)
Publish OB Standard v4.0
Standard
Draft
WGC
Draft 2
PLACEHOLDER - Start of Wave 1 – date TBC
Approval of Draft LTR
Publish Draft for industry consultation
* Appointment of a delivery lead has yet to be determined by JROC, plan predicated on assumption OBL will be selected. In the event of an alternative decision being taken, further planning will be required.
** Illustrative duration – actual timeframe will be instructed by the Regulators.
12
Ongoing alignment to the Disputes Framework
Define Eval criteria
Deep dive of leading solutions
Update / sign-off
Draft
WGC
Draft 2
09
13
07
JROC Board
04
JROC non-Order Programme Implementation Group
02
06
04
01
18
Funders Advisory Panel
08
09
04
Fin Com
15
24
22
19
19
VRP Implementation Group
31
28
25
30
20
17
VRP Working Group
12
25
08
05
19
03
17
31
14
28
12
26
Approval of MLA Roadmap
Requirements / analysis
Draft
Continued activities to further advance the MLA for Waves 2 & 3
Approval & publication of MLA v1.0
Update
Publish Guidance Notes
Sign-up phase**
Readiness / Build phase**
OBL providing support in the rollout of the MLA
Readiness
Propositional Bus Reqs defined
Approval of Final Draft of Rollout Guidelines
Approval of Final Draft of Disputes Framework
Approval of MLA final draft for broader IC
Updates if required
Updates if required
2025 governance forums and cadence to be defined
Evolve in readiness for Waves 2 & 3
Evolve in readiness for Waves 2 & 3
Illustrative timeline
Wave 2 draft requirements agreed
Eval potential solutions
Procurement process
Evaluation of MLA Operators
Business
Requirements
Define
Refine
Finalise operational business requirements
Approval of MLA Operator
Updates if required
Approval of Final
Draft of MLA Op Model
Publish sector definitions for Wave 1
Monitor and maintain up-to-date list of ASPSPs & TPPs
'expressions of interest’ and readiness​
Approval of Dispute solution
Blueprint recommendations analysis published to VRPWG
DEP – TRI Recommendations Report
to inform MLA Development
Define and implement arbitration approach and solution
07
Wave 1 Readiness
Report
WGC
Draft
WGC
Draft 2 / sign-off
Draft
Longer-term
Roadmap (LTR)
Iterative drafts shared with VRP PIG
Draft Wave 2 requirements
Core build complete ready for UAT
Wave 1 Disputes solution ready for go-live
UAT/release readiness
H/L & user story design
Build & QA
WGC
Draft 2 / sign-off
Draft
Roundtables
Readiness
MLA Roadmap Development (Inc. Wave 2+ Definitions) (timings TBC)
Advisory Group sessions with broader ecosystem
Socialisation
Implementation by ecosystem
Timings to be confirmed
Interim updates shared with VRPWG
PSR - Proposed commercial models presented for review
FCA - Additional premium APIs identified and presented to JROC with a recommendation as to which to progress in this workstream
Publish Wave 1 / Pilot Go Live Criteria
Draft
WGC
Draft 2
Delivery of the VRP Phase 1 Plan
Onboard external law firm support for MLA
KEY | 
WGC | Working Group consultation
IC | Industry consultation
 | ‘JROC Non-Order Workplan’ milestones

## Slide 21: Programme status update

## Slide 22: JROC Executive Exceptions Report (as at 30.09.24)
Previous: | Amber | Current: | Amber
Improving programme status, following WS5.4b having moved to an Amber status as a result of developing a workstream delivery plan. 1 workstream is reporting Red; WS1, and a further 3 workstreams are reporting Amber; WS2a, WS3 and WS5.4b. Summary reports on the status of data collection for WS1 and WS2a are being prepared by OBL to help inform a decision for JROC on next steps. The change request which has been prepared to rebaseline WS3 will be presented for a decision at JWIG on the 07/10. The draft WS4 ‘Information Flow Adoption Report’ was published to JROC for review. Mobilisation and detailed planning for the development of the Disputes mechanism solution continues for WS5.2. WS5.4a continues to plan, with operational requirements being managed through the cVRP WG, and feedback on the MLA Legal Sub-Group ToR is being reviewed by OBL. The evaluation of potential MLA operators continues to be progressed ahead of a recommendation being tabled to the JROC Board on the 07/11. The VRP WG (03/10) and FAP (04/10) are both scheduled for this week. |  |  | 
WS1 Levelling Up |  | ó |  | November deadline will not be met due to low volume and low-quality data.
WS2a Financial Crime Data |  | ó |  | November deadline at risk due to low volume and low-quality data.
Ws2b Financial Crime Tools (TRIs) |  | ó |  | On Track
WS3 Consumer Protection, (Disputes) |  | ó |  | Workstream behind plan. Not on critical path. Re-baseline to be agreed.
WS4 Information Flows |  | ó |  | Draft WS report has been published as planned.
WS5.1 Technical |  | ó |  | On Track
WS5.2 Disputes |  | ó |  | On Track
WS5.3 Industry Engagement |  | ó |  | On Track
WS5.4a MLA |  | ó |  | On Track
WS5.4b Commercial Framework |  | ñ |  | Moved to Amber from Red as Delivery plan developed but needs to be aligned with the PSR announcement.
Workstream RAG Status Exec Summary
Workstream and RAG |  | Reason for Non-Green Status |  | Action Plan |  | Action Owner |  | Action Target Completion Date |  | Status
WS1 Levelling Up |  | Reporting Red as OBL will not be able to produce the API Performance & Availability report with the requisite data by the end of November. |  | JROC to review report and to decide to proceed with a mandatory or voluntary data request. See previous report for completed actions. |  | JROC |  | TBC |  | Open
WS2a Financial Crime Data |  | Reporting Amber as there is a risk of not receiving substantive data in time to fulfil the workstream deliverables, however, confidence in expected data is higher than for WS1. |  |  |  |  |  |  |  | 
WS3 Consumer Protection, (Disputes) |  | Reporting Amber – workstream running behind plan as pre-work was required to clarify the WS scope coupled with focusing efforts on mobilising the programme and on progressing WS5 activities. The workstream is not on the overall critical path for the programme. |  | Identify and re-focus resources to WS3 Create revised plan and share with FCA OBL to Raise CR to JWIG to rebaseline the workstream JWIG approval of the change request |  | OBL OBL OBL JWIG |  | 06/09/24 20/09/24 20/09/24 07/10/24 | O | Complete Complete Complete Open
WS5.4b Commercial Framework |  | Reporting Amber (improved position from Red last week), delivery plan has been developed, however, needs to be aligned with the PSR announcement due mid-October, once received a change request will be produced to rebaseline the workstream. |  | Create delivery plan including the governance process and timings and share with FCA/PSR Determine that critical path date by which the Commercial Framework needs to be in place so that it can be built into the Wave 1 MLA so that the current timelines can be met Raise CR to JWIG to baseline the workstream (subject to alignment with PSR announcement) |  | OBL OBL OBL / JWIG |  | 27/09/24 27/09/24 TBC |  | Complete Complete Open
Non-Green Return to Green Plan
Workstream |  | Decision Required |  | JROC Decision Date |  | Decision Status |  | Decision Outcome |  | Date of Decision
Levelling Up |  | JROC to determine next steps to increase the data to complete an effective evaluation |  | TBC |  | Open |  | TBC |  | TBC
Financial Crime Data |  |  |  |  |  |  |  |  |  | 
MLA |  | Choice of operator for the MLA. Decision on whether the MLA and Disputes Operator needs to be the same. Subject to PSR consultation, what the role of the MLA operator will be in the commercial framework development. Determine the commercial framework (price clause) for inclusion in the MLA for Wave 1. |  | 07/11/24 07/11/24 TBC TBC |  | Open Open Open Open |  | TBC |  | TBC
JROC Decision Log
JROC Programme Delivery Headline Summary
To be updated

## Slide 23: Workstreams 1-4 Status Report (as at 30.09.24)
RAG Definitions: | Overall (Based on Time, Quality and Risk RAGs) | Time/Schedule (on track to meet agreed deadlines) | Quality (confidence that the deliverables will meet JROC expectations) | Risks (risk to delivery)
Workstream RAG | This Week | Last Week
 | Overall | Overall
1. Levelling up | R | R
2a. Financial Crime Data | A | A
Workstream RAG | This Week | Last Week
 | Overall | Overall
2b. Financial crime tools | G | G
3. Consumer Protection | A | A
4. Information Flows | G | G
Workstream | RAG Status* |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
1. Levelling up availability and performance | R | R | R | A | Reporting Red as OBL will not be able to produce the API Performance & Availability report with the requisite data by the end of November. OBL has processed data submissions since mid-Feb, as per plan, but low levels of participation and incomplete data observed. Requirement of 6 consecutive months of data for 60-80% of market will not by fulfilled by the Nov deadline. 25/09 FCA call: OBL presented the latest status update (7 submissions, poor quality/completeness incl. heatmap). FCA acknowledged there is nothing OBL can do at this stage and asked for a high-level WS1 summary report. | WS1: produce a summary report by 04/10 (as requested on 25/09 call) WS2a: produce headlines from data gathered so far by 04/10 (as requested on 25/09 call) JROC decision on next steps based on the reports summarising TPP and ASPSP feedback. | Prepare the WS1 & 2a reports by 04/10 Support participants with any MI questions. Working with JROC on next steps relating to voluntary data request.
2a. Financial Crime Data | A | A | A | A | Reporting Amber, noting a risk of not receiving 6 month of data to fulfil the workstream deliverables. Quality RAG has improved from Red to Amber now that the CMA9 who stopped submitting data in May are now resuming submissions as more ASPSPs are submitting. They agreed to submit the missing months by early Oct, which would achieve 60% coverage of the market represented and allow OBL to RAG Time and Quality to Green. 25/09 FCA call: OBL presented the latest status update. FCA requested a report on headlines from the data collected so far. |  | 
2b. Financial crime tools (e.g. TRIs) | G | G | G | A | Reporting Green - No changes The data phase continues to run smoothly, with TRIs being received as expected. | The primary focus for Sep and Oct will be on TRI volumes and efficacy in preparation for the final report and conclusions. Pilot ASPSPs are preparing to share an interim update prior to the final report. | Collating feedback and statuses from pilot banks to produce and share interim update with JROC.
3. Consumer Protection (Disputes) | A | A | G | A | JROC feedback on the scope document has been received and updated, and upon final JROC sign-off the materials will be shared with JWIG and roundtable attendees, target w/c 30.09. A decision of the CR to rebaseline the workstream is now tracking to JWIG on the 07/10. Roundtable invites have been sent – first set will be October 8/9 and second set October 24/25, with time in between and after the second set for additional sessions if needed – moderate level of sign-ups (17 organisations at time of writing) so OBL are reaching out directly to increase engagement. Analysis is underway and OBL are talking with Pay.UK and PSR about existing research we can use to fast track our analysis. | Approval of workstream scope and CR First pack for roundtable Second pack for roundtable | Analysis and preparation for roundtable 1
4. Information Flows | G | G | G | G | The draft WS4 ‘Information Flow Adoption Report’ was published to JROC for review on the 27/09. OBL received input from all CMA9, 2 non-CMA9 directly plus 7 through Participant Support, and 8 TPP; providing a satisfactory level of coverage and allowing conclusions to be drawn. | Final report to be published w/e 04/10. | Respond to any JROC feedback on the draft report.
To be updated

## Slide 24: Workstream 5 Status Report (as at 30.09.24)
Workstream |  | RAG Status* |  |  |  | Key Progress Updates | Upcoming Deliverables, Meetings and Focus Areas | Next week
 |  | Overall | Time | Quality | Risks | Include RAG rationale and action plan and any new risks or issues | Key Milestones/Deliverables due in next 4 weeks (as per plan) | Focus Areas for Next Period
5.1. Technical |  | G | G | G | G | Continues to report Green. The workstream is tracking technical requirements on PISPs and ASPSPs under the MLA, this is being worked through alongside propositional & operational MLA requirements. As per MLA stream, the last of the propositional elements has been presented to WG and operational requirements are being covered. Requirements for later waves are being picked up through a combination of MLA requirements that have been discounted from Wave 1 but are relevant to Wave 2 or a later wave; or through post-pilot VRP blueprint requirements. | Track technical requirements. Support MLA stream with MLA papers. Continue refining longer-term roadmap for waves 2+, to bring to IG at future date. | Support & monitor MLA proposition elements. Support & monitor Operational MLA requirements. Continue populating longer-term roadmap for Wave 2+. Consider benefit of technical implementation workshops.
5.2. Disputes |  | G | A | G | G | Workstream maintaining a Green status Detailed planning underway based on the Disputes mechanism solution approved by JROC. Amber sub-RAG reported against the time component until the detailed planning activities have concluded and the existing plan of record has been validated. Unhappy paths catalogue shared with WG on 19/09, with feedback by 03/10. | OBL to commence legal analysis of liability position of each identified unhappy path. Clarification of whether MLA Disputes are in scope with WG Conduct detailed design activities ahead of build phase | Internal approval to proceed. Development of liability position for each Unhappy Path.
 |  |  |  |  |  | Disputes Solution – development swimlane Continuing with the planning and mobilisation of the project, with particular focus this week on build/milestone planning and solution design. | High level implementation plan baselined High level user stories and design agreed | High level implementation plan baselined High level user stories and design agreed
5.3. Industry Engagement |  | G | G | G | G | Reporting Green. Work progressing with wider community from September. ‘WS5 info session’ held 30/09, 36 firms in total attended. | Update status of interested parties to VRP IG. Facilitate the ‘WS5 ecosystem info session’ (30/09). | Update status of interested parties to VRP IG (on-going).
5.4. MLA & Commercial | 5.4a MLA | G | G | G | A | Reporting Green overall, although risk noted to reflect the uncertainty around the delivery timing of the commercial framework/model (until WS5.3b CR approved). Engagement letter with Addleshaw Goddard (AG) signed. Discussions on MOU with Pay.UK still under discussion. Pay.UK have not provided their feedback/comments. Feedback on the Terms of Reference for the MLA Legal Sub-Group (LSG), i.e. smaller number of participants concept received from the VRPWG and currently under review by OBL. Kick-off call with AG held and draft Heads of Terms reviewed, and comments fed back to AG for finalisation. The first group of operational requirements is currently with the cVRP WG for comment by 03/10 The second group of Op reqs is due to be presented at the 03/10 cVRP WG. The final 2 op req groups will be tabled at the later Oct cVRP WG meeting. | MOU with Pay.UK signed. LSG formed and starting to operate from October 10. AG will attend/lead this LSG. Heads of Terms finalised and shared with LSG at 10/10 LSG meeting. Regular meetings held between AG and OBL/Pay.UK to progress drafting of MLA v1.0. Business Requirements finalised and provided to AG to incorporate into MLA drafting; significant progress on Operational requirements with all proposals sent to WG by end-October. | Continue to work with AG to progress MLA 1.0 drafting. Review and provide feedback on drafts as and when provided by AG. Develop plan to share and consult with VRP WG on MLA 1.0 (draft 3) by end of October. Coordinate and chair LSG meetings to progress MLA drafting work and bringing back relevant items to VRP WG for emndorsement/consulation.
 | 5.4b Comm Framework | A | A | G | A | Reporting Amber (improved position from Red last week), delivery plan has been developed, however, needs to be aligned with the PSR announcement due mid-October, once received a change request will be produced to rebaseline the workstream. | Commence procurement activities to onboard external consultancy support. Raise CR to JWIG to baseline the workstream. | Raise CR to JWIG to baseline the workstream (subject to alignment with PSR announcement)
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.1. Technical | G | G
5.2 Disputes | G | G
Workstream RAG | This Week | Last Week
 | Overall | Overall
5.3 Industry Engagement | G | G
5.4a MLA | G | G
5.4b Commercial Framework | A | R
To be updated

## Slide 25: Return to Green (RTG) Status Report (as at 30.09.24)
Workstream | RAG Status | Reason for non-Green status | Return to Green plan List out specific actions, dates, and owners (including any non-OBL action owners) |  |  | Overall RTG date
 | Overall | Detailed Description/Reason - should be comprehensive and clear | Itemised action plan | Action owners | Action target completion data | 
WS 1 – Levelling Up | R | Reporting Red as OBL will not be able to produce the API Performance & Availability report with the requisite data by the end of November. Non-Order workplan objective is to analyse 6 consecutive months of data representing 60-80% of the market by 01/11. Handful of submissions received to date, incomplete data set, quality issues, and far from reaching the market representation threshold. Enough useable overlapping data across submissions is required to produce a meaningful analysis. Keeping in mind this is a voluntary submission exercise. | Flagged Nov. deadline risk to JROC. JROC will decide next steps and potential impact on timeline based on TPP’s responses to WS1 survey. TPP roundtable took place on 01/08 to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. Survey sent to 23 TPPs, with a 15/08 deadline. Ecosystem feedback summary report sent to JROC w/c 26/08 subject to JROC requirements. JROC’s decision on FCA data request, voluntary vs. mandatory, scope (number of non-CMA9 and TPP returns OBL can expect (resourcing & budget implications)), data period requested (last 6M vs. monthly as of start date), expected date of first submission given to participants. Gather TPPs & ASPSPs intentions to submit data by the start date. Reassess impact on ‘non-order workplan’ timeline: if monthly submissions, will require date when OBL starts getting data for 60-80% of market (note: this might later than the start date) + 6M. Agreement on revised timeline and get budget to resource work (external contractors and/or API build. | OBL OBL OBL OBL JROC JROC OBL JROC or JWIG | Complete Complete Complete Complete TBD TBD TBD TBD | TBD
WS2a - Financial Crime Data | A | Reporting Amber, noting a risk of not receiving substantive data in time to fulfil the workstream deliverables. However, confidence increased this week as 1 CMA9 agreed to resume submissions and submit missing May-Aug data. This would bring us to 60% of the market represented and allow us to RAG Time and Quality to Green. | Flagged Nov. deadline risk to JROC. JROC will decide next steps and potential impact on timeline based on ASPSP’s responses to WS1 survey. ASPSP roundtable took place on 01/08 to mitigate the data risk and to help inform JROC on next steps, incl. potential FCA 'voluntary data request’. Survey sent to 16 ASPSPs, with a 15/08 deadline. Ecosystem feedback summary report sent to JROC w/c 26/08. Receiving missing months (May-Aug) from 1 CMA9 who had stopped submitting. Receiving confirmation from submitting firms that they will submit Sep data by 21/10. Proposal would be to return to Green once items 5 & 6 are completed. JROC’s decision on FCA data request, voluntary vs. mandatory, scope (number of ASPSP returns OBL can expect (resourcing & budget implications)), data period requested (last 6M vs. monthly as of start date), expected date of first submission given to participants. | OBL OBL OBL OBL OBL JROC OBL JROC or JWIG | Complete Complete Complete Complete 08/10/24 08/10/24 08/10/24 TBD | TBD
To be updated

## Slide 26: Return to Green (RTG) Status Report (as at 30.09.24) – 2/2
Workstream | RAG Status | Reason for non-Green status | Return to Green plan List out specific actions, dates, and owners (including any non-OBL action owners) |  |  | Overall RTG date
 | Overall | Detailed Description/Reason - should be comprehensive and clear | Itemised action plan | Action owners | Action target completion data | 
3. Consumer Protection (Disputes) | A | Workstream running behind plan as pre-work was required to clarify the WS scope coupled with focusing efforts on mobilising the programme and on progressing WS5 activities. The workstream is not on the overall critical path for the programme. Change request has been shared with the FCA ahead of being issued to JWIG to rebaseline the workstream delivery by 1-month. Upon approval of the CR, the workstream will return to Green. | Identify and re-focus resources to WS3 Create revised plan and share with FCA OBL to Raise CR to JWIG to rebaseline the workstream JWIG approval of the change request (aligned to the meeting on the 07/10). | OBL OBL OBL JWIG | Complete Complete Complete 07/10/24 | 07/10/24
5.4b Comm Framework | A | Reporting Amber (improved position from Red last week), delivery plan has been developed, however, needs to be aligned with the PSR announcement due mid-October, once received a change request will be produced to rebaseline the workstream. | Create delivery plan including the governance process and timings and share with FCA/PSR. Determine the critical path date by which the Commercial Framework needs to be in place so that it can be built into the Wave 1 MLA so that the current timelines can be met. Raise CR to JWIG to baseline the workstream (subject to alignment with PSR announcement). | OBL OBL OBL / JWIG | Complete Complete TBC | TBC
To be updated

## Slide 27: MLA Operator – latest thinking
To be updated

## Slide 28: Progress to date
Determining the wave 1 MLA operator is a key decision for the VRP programme. The optimal operator needs to be identified in time to allows the wave 1 transactions to flow in H1 2025, as per the agreed programme objectives.
In light of this we have made the following progress:
  Set out the proposed timeline/approach to the VRP WG, FAP and JWIG on 5 September
  Outlined the proposed operator options and evaluation criteria to the VRP WG
  Received feedback from ten participants on the operator options and evaluation criteria. This feedback also contained initial views on their operator choice
  Outlined the functional capabilities required of the wave 1 MLA operator and awaiting feedback
In light of the feedback OBL and Pay.UK have submitted a paper for the VRP WG to review on 3 October which provides an overview of how the thinking on the MLA operator is progressing. This is the next stage in the process towards a recommendation being presented to the JROC Board on 7 November. A summary of the paper is on slides 31 and 32.

## Slide 29: Evaluation criteria and assumptions
Management of liabilities
Suitability of the management and governance of the organisation
Future development for waves 2+, etc.
Legal practicalities relating to the organisation in operating the MLA
MLA fit with JROC’s longer-term plans for the Future Entity
Ease of set-up
Alignment with capabilities of the organisation
Fit with core purpose of the organisation
Wider strategic implications for each organisation
Cost (set-up and run)
1
2
3
4
5
6
7
A successful solution should be justified based on the following criteria:
8
9
10
Notes: Could be write down an interesting fact that people don’t know about you

## Slide 30
Options – 1/2
Pay.UK would be a contracting party to the MLA acting as the Wave 1 MLA Operator, discharging this role alongside their other responsibilities as the operator of the UK’s faster payments and BACS retail payment systems
The Payment Systems Regulator (PSR) in their Call for Views on VRPs (CP/23/12) identified Pay.UK as a potential option to be the MLA operator
Robust governance processes would be required to govern how Pay.UK discharges these responsibilities alongside their existing ones
Pay.UK and OBL would both be contracting parties to the MLA acting jointly as the Wave 1 MLA Operator
Other than increased roles/responsibilities to manage and operate the MLA, there would be no change in the existing structure and governance arrangements of either of these entities
Robust governance processes would be required to govern how OBL and Pay.UK discharges these responsibilities alongside their existing ones
OBL in its current form would be a central contracting party to the MLA alongside its existing Order related obligations
It would also potentially operate the DMS.
The Payment Systems Regulator (PSR) in their Call for Views on VRPs (CP/23/12) identified OBL as a potential option to be the MLA operator
Robust governance processes would be required to govern how OBL discharges these responsibilities alongside their existing ones
Set against these evaluation criteria, we have identified these potential options:
3. Joint Operators (OBL and Pay.UK)
Pay.UK
2. OBL
Notes: Could be write down an interesting fact that people don’t know about you

## Slide 31
Options – 2/2
OBL and Pay.UK could incorporate a new company as a special purpose vehicle (SPV) in which, for example, they could be 50/50 owners. This new SPV would be a contracting party to the Wave 1 MLA as the Wave 1 MLA Operator
This would be a more formalised approach of Option 3
This entity would seek to leverage the capabilities and resources of OBL and Pay.UK (and potentially other third parties) procured through intercompany outsourcing arrangements. Pay.UK currently operates this model for UTSP service
Robust governance processes would be required to govern how this entity discharges these responsibilities
4. NewCo (50:50 owned, OBL and Pay.UK)
A new entity would be created to fulfil the role of the Wave 1 MLA Operator and would be a contracting party to the MLA
A possible corporate structure would be for this new entity to be limited by guarantee
NewCo would seek to leverage the capabilities and resources of OBL and Pay.UK (and potentially other third parties) procured through intercompany outsourcing arrangements
Robust governance processes would be required to govern how the NewCo discharges these responsibilities
5. NewCo (Legally independent)
Notes: Could be write down an interesting fact that people don’t know about you

## Slide 32: Proposed functional capabilities presented to the VRP WG for feedback
A. Monitoring compliance with the MLA
Data analysis
Complaints function
Investigation / assessment of potential compliance breaches
Impact assessment / decision making / sanctions
B. Billing
Setting tariffs / fees
Calculation of money owed – scheme fees and inter participant fees
Ensuring settlement
C. Intra-party dispute management
Contracting with the supplier of the dispute system
Maintaining liabilities arrangements and ensuring consistent outcomes
Where disputes are not resolved providing arbitration
D. Risk Mitigation
Ensuring risks to the operator are understood and mitigated e.g. business risk
Ensuring plans and processes are in place to address ecosystem risk e.g. participant insolvency; large technical failure
Mitigating legal risk
Mitigating supplier and operational risks
Understanding the rules and requirements of the Operator in relation to GDPR
E. New participant onboarding
Assessing joining applications against access criteria
Legal co-ordination of MLA signatories
Accreditation of new participants meeting MLA technical requirements
Co-ordination / on-boarding new participants
F. MLA Maintenance and iteration
Own, maintain and update the rules/MLA and any relevant requirements
Agree and operate an MoU/SLA with OBL and Pay.UK (where relevant)
Undertake the work to move to Waves 2 and 3.
Assess waivers and administer them
G. Change management / co-ordination
Agreeing and administering ecosystem wide change/update cycles
Agreeing/monitoring participant specific change cycles
Implementing change-freeze windows
H. Crisis management / co-ordination of resolution
Communication and co-ordination of ecosystem issues e.g. cyber attack
Co-ordination of post crisis activities e.g. money has been returned

## Slide 33: Feedback to date from VRP WG
At the VRP WG on 5 September we presented a paper on the operator options and the evaluation criteria. The paper also invited initial views on the choice of operator. Ten organisations responded.
The key messages were:
Two firms expressed a preference for a commercial organisation to be the MLA operator
There was some preference for the NewCo option. One notable firm did support this, but would also like to see an RFP for future waves/evolution
The TPPs suggested that OBL should be the wave 1 MLA operator based on having the core skills and it being an expedient solution
Some concern from the banks and others that we are putting speed/expediency ahead of other/longer-term considerations
One TPP suggested that an industry led SPV is developed to run the MLA for waves 2+, albeit there were no details on what this would entail.
Another TPP suggested that the MLA could be a wholly owned subsidiary of Faster Payments Scheme Limited run by outsourced OBL staff.
Some suggestions were for broadening the evaluation criteria. A number of the banks raised the issue of liabilities.

## Slide 34: ‘Direction of travel’ thinking on the MLA operator for the VRP WG on 3 October (1/2)
It is clear that the issue of potential liabilities which may be created for the CMA9 banks from OBL operating the Wave 1 MLA or even having some form of control of the MLA Operator (e.g. x% holding of a JV) is a hurdle. It appears this is a hurdle that in effect becomes the first evaluation criteria that needs to be assessed and hence narrows down the options before other criteria are brought into the assessment.
There are also several criteria which Pay.UK will need to work through before being able to confirm its ability to take on any role in the MLA.
In reviewing Options 1 (Pay.UK being the sole operator) and 2 (OBL being the sole operator) we do not consider either organisation has the full range of capabilities to undertake being the MLA Operator on their own.
In light of the above considerations and the feedback/discussions to date we see options 3 (joint operator option), 4 (SPV owned by Pay.UK and OBL) and 5 (NewCo) as the options with greatest merit. Hence, we propose to focus on developing more detailed thinking on Options 3, 4 and 5 as the next steps. Alongside this, we will continue to review the liability position to assess whether a solution which allows more direct OBL involvement can be found.
We see Options 3 (joint operator option) and 4 (SPV owned by Pay.UK and OBL) as bringing together the complementary strengths and capabilities of both organisations to act as the MLA operator. With Option 3 we see both Pay.UK and OBL as being central signatories to the MLA. By having a separate company (i.e. option 4) there is a clear, single signatory to the MLA. We need to understand whether OBL having a formal share of the SPV leads to any liability issues and whether this can be mitigated by the degree of separation and/or other legal means. This will form part of the next round of thinking.

## Slide 35: ‘Direction of travel’ thinking on the MLA operator for the VRP WG on 3 October (2/2)
Option 5 (NewCo) provides a clear separation between OBL and the NewCo which allows the liabilities concerns of the CMA9 to be addressed. This will be tested in the next round of analysis. By creating a NewCo it can have a clear brief and solely focus on running the VRP scheme. It is anticipated that the NewCo would source required capabilities from Pay.UK and OBL via intercompany outsourcing agreements allowing it to benefit from the respective capabilities of both organisations. As part of the analysis, we will need to understand more about areas such as governance, funding and time to establish. At this point, we do not believe Option 5 precludes future options for any successor ‘Future Entity’. We understand that the NewCo can be established relatively quickly and in line with the wider VRP timeline. This assumption will be reviewed in more detail.
We will also consider iterations of the options. One such option could be to allow a NewCo and Pay.UK to form a joint venture to operate the MLA. This would address the CMA9 liability concerns, whilst allowing direct involvement from Pay.UK. A further evolution was suggested in the feedback by one firm that some TPPs and Banks may want to take a direct shareholding interest in the legal entity to be set up for the Wave 1 MLA Operator. We consider this to be an evolution of the original NewCo option and see merit from having TPPs and Banks having a direct involvement in the MLA Operator. It would be important to have both Banks and TPPs involved to provide balance in the ownership structure. We therefore propose to analyse these iterations in more detail.
Some firms commented that they believed an expedient solution was being given greater weight than long-term considerations and hence could lead to the wrong decision being made. We understand these concerns and acknowledge that that remains a risk, however, we believe it is important to balance that risk against the need to focus on developing a solution which is aligned with the broader programme objectives and timelines. Further, the MLA Operator choice is focused primarily on allowing Wave 1 transactions to flow. This will allow for a test and learn solution to be adopted to create learning and enhancements for Waves 2 and beyond. Importantly, any decision for Wave 1 does not preclude alternative options being considered for Wave 2+.
Some firms suggested that a commercial tender should be undertaken for the Wave 1 MLA Operator to allow third parties to pitch for the role. Whilst we do see some merits in this proposal, we do not consider this to fit with the timeline for the VRP programme given the extensive time, resources and effort that that process would entail, and we consider would be more appropriate to explore as part of the review for the future waves.

## Slide 36: MLA legal drafting – update

## Slide 37: WS3 – roundtable update

## Slide 38: AOB